## Tasks
Task ID | Task Name | Task Type | Description | Owner | Assignee | Approver1 | Predecessor | Start Day | End Day | Instructions | Cost Center
T001 | Close subledgers | Basic | Close AP and AR | controller | ap.lead | controller |  | -2 | -1 | Run close in ERP | 100
T002 | Load trial balance | Data Load | Load TB into FCCS | controller | fin.analyst | controller | T001 | 0 | 0 |  | 100
T003 | Run consolidation | Consolidation |  | controller | fin.analyst | cfo | T002 | 1 | 1 |  | 200
T004 | Intercompany reconciliation | Basic |  | controller | ic.analyst | controller | T002 | 1 | 2 |  | 200
T005 | Review results | Review | CFO review | cfo | controller | cfo | T003, T004 | 2 | 3